## Slide 1
Proposed plan · docs/MOBILE-ROADMAP.md (planning date 2026-09-13, dependency update 2026-09-15) · HEAD 1ed17eb + working tree
Mobile · 1
iOS & Android
delivery
roadmap
How Modeer could reach phones without weakening what already works.
PROPOSED · NOTHING BUILT
Prepared 2026-09-15
For the owner and the incoming mobile team
Mobile starts only after the web release gates close.
First milestone: a two-platform prototype that signs in, streams, survives a dropped connection and rejects a revoked session.
Notes: AUDIENCE: the owner and the incoming mobile/engineering team.
STATUS: everything in this deck is PROPOSED. No mobile app, native authentication endpoint, store account, bundle/application ID or signing identity exists. Nothing here is evidence that native features are implemented.
SOURCES: docs/MOBILE-ROADMAP.md (planning date 2026-09-13; dependency update 2026-09-15), docs/PROJECT-REPORT.md, docs/launch-rehearsal-2026-09-14.md, docs/quality-evidence-2026-09-15.md, backend and frontend source at HEAD 1ed17eb plus the uncommitted working tree.
Time-sensitive Apple, Google and Expo requirements were rechecked against official pages on 2026-09-15 (see the store slide and appendix). The React Native framework recommendation could not be re-fetched on 2026-09-15 and keeps its 2026-09-13 documented date.
Effort figures are ranges under stated assumptions, not dates, quotes or budgets.
SOURCES (repository paths are relative to the root): Proposed plan · docs/MOBILE-ROADMAP.md (planning date 2026-09-13, dependency update 2026-09-15) · HEAD 1ed17eb + working tree
BASELINE: branch fixes/launch-readiness-20260911, HEAD 1ed17eb5748d948a541f0e76a7fabcddd094534d plus the uncommitted working tree; deck prepared 2026-09-15.

## Slide 2
STARTING POINT
Mobile depends on the web release gates
docs/launch-rehearsal-2026-09-14.md · docs/quality-evidence-2026-09-15.md · docs/MOBILE-ROADMAP.md §1
Mobile · 2
Web today
Streaming chat with 4 reply states
Shared + private memory, goals
Passwords, recovery codes, revocation
Export and in-app deletion
Verified locally, not on a real host
Still open
Answer quality: 27 pass · 11 fail · 1 ungraded
Real domain, remote backups, alert receipt
Phones and screen reader untested
Fixes still uncommitted
Mobile
No app, API or store accounts yet
Starts with a small feasibility spike
Native password accounts wait for the gates
UNRESOLVED DEFECT
OPERATIONAL GATE
PROPOSED
Notes: WHAT EXISTS (web, implemented; locally verified 2026-09-14/15): FastAPI backend with cookie sessions, password/recovery codes, POST/SSE streaming chat with four completion states, shared/private memory, goals, account export/deletion. Local production rehearsal: 351 backend tests in the locked image (2 recovery races on PostgreSQL 16), 23 HTTPS browser checks, 25 axe scans with zero findings, 10 operations checks, 13 live journey checks. These numbers are separate evidence, not a combined score.
STILL OPEN (must close before native password accounts are exposed):
- Unresolved defect: answer quality — 27 automated passes, 11 failures, 1 unavailable grade across 39 live answers, with manual checks finding both judge errors and missed defects.
- Operational gates: real host/domain/TLS, genuinely remote backup + scheduler + restore, alert receipt by a person, legacy memory audit.
- Coverage gaps: physical devices, human screen reader, load/multi-worker, real network disconnect.
- Release hygiene: the Sept 13–14 fixes are in an uncommitted working tree on top of 1ed17eb.
NATIVE MOBILE: proposed only; no code, accounts or signing identities.
SOURCES (repository paths are relative to the root): docs/launch-rehearsal-2026-09-14.md · docs/quality-evidence-2026-09-15.md · docs/MOBILE-ROADMAP.md §1
BASELINE: branch fixes/launch-readiness-20260911, HEAD 1ed17eb5748d948a541f0e76a7fabcddd094534d plus the uncommitted working tree; deck prepared 2026-09-15.

## Slide 3
SCOPE
The mobile MVP mirrors the web journeys
docs/MOBILE-ROADMAP.md §3 · backend routes (auth, chat, conversations, memory, goals, briefings, users)
Mobile · 3
Journey | Already on the web | Mobile MVP work
Access | Password or key · recovery codes | Native forms · secure session · code handling
First use | Onboarding with Modeer | AI-sharing consent before the first request
Home & team | Hero · specialists · Today | Native tabs and portrait panels
Chat | POST + SSE · 4 reply states | Streaming transcript · reconnect reconciliation
Memory & goals | Shared/private facts · goals | Same controls, server-confirmed writes
Account rights | Export · delete · sign out all | In-app deletion · local purge
AI reports | Not built | Report action + operator triage (store requirement)
Not in the MVP
Ask My Team
Voice, widgets, attachments
Push reminders
Health, calendar, email links
Payments, social login
Offline AI answers
PROPOSED SCOPE
Notes: MVP (proposed) = a private personal AI workspace, no public content, no external actions.
Mapping to existing foundations:
- Sign in / optional signup / recovery → password/key routes, recovery codes, epoch → native forms, secure sessions, deliberate recovery-code handling, accessible validation.
- First use → Modeer onboarding, shared facts, profile → concise privacy/AI-sharing explanation with explicit required consent, first chat, inspectable memory.
- Home / Team → hero, featured specialists, Today, ten identities → native navigation and portrait panels.
- Chat / history → POST SSE, conversation API, four reply states → streaming native transcript, keyboard-safe composer, history, Continue/Try again, reconnect reconciliation.
- Memory → shared/private CRUD, pinning, automatic-memory switch.
- Goals / Today → goal CRUD and deterministic briefing (no calendar claims).
- Account rights → export, deletion, sign-out-everywhere → secure share flow, in-app deletion, local-cache purge, revocation handling.
- AI output concerns → no reporting workflow exists → in-app report action, server intake and operator process (required before Google Play release).
OUT OF MVP (optional, not implied commitments): Ask My Team UI, voice, push reminders, widgets, HealthKit/Health Connect, calendar/email connections, camera/document uploads, autonomous actions, payments, social login, offline AI generation. Do not request contacts, microphone, health or location permissions without an implemented feature that needs them.
SOURCES (repository paths are relative to the root): docs/MOBILE-ROADMAP.md §3 · backend routes (auth, chat, conversations, memory, goals, briefings, users)
BASELINE: branch fixes/launch-readiness-20260911, HEAD 1ed17eb5748d948a541f0e76a7fabcddd094534d plus the uncommitted working tree; deck prepared 2026-09-15.

## Slide 4
TECHNOLOGY OPTIONS
React Native with Expo — if the team fits
docs/MOBILE-ROADMAP.md §2 · docs.expo.dev expo/fetch (SDK 57 page, checked 2026-09-15) · reactnative.dev (documented 2026-09-13)
Mobile · 4
React Native + Expo
Reuses TypeScript, types, tokens, art
One mobile codebase
Streaming fetch documented by Expo
Recommended, after a device spike
Flutter
Reuses APIs, assets, design intent
New language and UI layer
Great rendering control
Viable with a Flutter team
Native iOS + Android
Full platform control
Two clients to build and keep in sync
More release coordination
Only with platform specialists
Assumption: team skills are unknown — the owner should confirm before committing to a framework. A WebView wrapper is a demand test, not the product.
Notes: RECOMMENDATION (documented engineering inference, not a verified team fact): a separate React Native app using Expo and TypeScript, consuming the existing FastAPI backend; keep the web app; preserve the approved design; start with a physical-device auth + streaming prototype, not a full port.
WHY: existing React/TypeScript codebase, modest screen count, server-hosted AI, one shared mobile implementation.
STAFFING ASSUMPTION: actual team availability and native experience are UNKNOWN. Revisit if the owner already has an experienced Flutter or native team (owner decision).
OPTIONS
- React Native + Expo: reuses TypeScript knowledge, domain types, pure utilities, artwork and tokens; native views replace DOM/CSS; Expo services are optional infrastructure choices.
- Flutter: reuses APIs, assets and design intent; client moves to Dart; strong rendering control for comic panels; attractive with an experienced Flutter team.
- Separate native (SwiftUI + Kotlin/Compose): maximum platform control; two UI/state/transport implementations; prefer only with dedicated platform engineers.
- WebView wrapper: acceptable as a demand probe only; keyboard, navigation, accessibility, secure storage, interrupted networks and store requirements still need real work.
VERIFICATION: Expo's expo/fetch documentation (SDK v57.0.0 page, fetched 2026-09-15) shows reading resp.body with getReader() for text/event-stream — a candidate transport, not proof Modeer's POST/SSE works on a device. React Native's "use a framework such as Expo" guidance is carried from the 2026-09-13 documented check; reactnative.dev could not be fetched on 2026-09-15. Pin a compatible Expo/React Native/React set at implementation time; do not copy web package versions.
SOURCES (repository paths are relative to the root): docs/MOBILE-ROADMAP.md §2 · docs.expo.dev expo/fetch (SDK 57 page, checked 2026-09-15) · reactnative.dev (documented 2026-09-13)
BASELINE: branch fixes/launch-readiness-20260911, HEAD 1ed17eb5748d948a541f0e76a7fabcddd094534d plus the uncommitted working tree; deck prepared 2026-09-15.

## Slide 5
BACKEND REUSE AND REQUIRED API WORK
Reuse the backend; add what phones need
docs/MOBILE-ROADMAP.md §4–6 · backend/app/core/auth.py · api/routes/auth.py · frontend/src/features/chat/useChatStream.ts
Mobile · 5
Reuse as-is
Accounts, passwords, recovery codes, epochs
Streaming runtime and 4 reply states
Memory scope, validation, consent switch
Quotas and refunds
Export and deletion services
Prompts, models, keys stay on the server
Build first (P0)
Native tokens: access + rotating refresh, per device
Idempotency key and durable turn record
Status endpoint to reconcile after reconnect
Stable error codes
Cursor pagination
AI-report intake · web deletion page
PROPOSED
Notes: REUSABLE (implemented today): account model, password and recovery verification logic, epoch revocation, per-account quotas and refunds, streaming runtime and completion states, memory scope and validation, goals and briefings, export and deletion services, observability and readiness. Provider keys, prompts, model selection, extraction and quota enforcement STAY on the server.
Also reusable as specifications: tests, artwork (after rights review), palette/typography, agent identity wording, domain types (validated against a versioned development schema artifact — do not reopen production Swagger).
NOT DIRECTLY REUSABLE on mobile: browser components, Tailwind classes, next/navigation, Next image/font loaders, window.location, DOM Markdown rendering, and the current chat hook (it mixes network parsing with React/browser state and drops memory error fields — extract a tested transport/event parser only after fixing its contract).
REQUIRED API WORK (proposed, P0):
1. Native session contract: short-lived bearer access tokens + rotating refresh credentials backed by per-device server records; hashed refresh storage; token-family reuse detection; atomic rotation; device logout; sign-out-everywhere and password/recovery revocation; epoch (or equivalent) check on every request. Prefer an established, reviewed implementation. Never weaken browser cookie/Origin protections.
2. Operation identity: client request ID/idempotency key + payload fingerprint; durable turn record with atomic claim and lease; status endpoint to reconcile after reconnect.
3. Stable error codes (auth, allowance, provider limits, interruption, memory failure) with retry_after.
4. Cursor pagination for conversations/messages.
5. Versioned API/schema artifact; AI-output report intake; external account-deletion web resource.
SOURCES (repository paths are relative to the root): docs/MOBILE-ROADMAP.md §4–6 · backend/app/core/auth.py · api/routes/auth.py · frontend/src/features/chat/useChatStream.ts
BASELINE: branch fixes/launch-readiness-20260911, HEAD 1ed17eb5748d948a541f0e76a7fabcddd094534d plus the uncommitted working tree; deck prepared 2026-09-15.

## Slide 6
AUTHENTICATION, STORAGE, REVOCATION, LINKS, DELETION
Native sessions without weakening the web
docs/MOBILE-ROADMAP.md §5 · docs.expo.dev SecureStore (checked 2026-09-15) · Apple 5.1.1(v) · Google Play account deletion (checked 2026-09-15)
Mobile · 6
Sign in
password or key
Issue tokens
access + refresh · device record
SecureStore
small credential only
API call
access token · epoch check
Refresh
rotate · detect reuse
Revoke
logout · sign out all · password change · recovery · deletion
Rules
Never relax browser cookie or Origin checks
Uninstall is not a logout; verify session at launch
No secrets or chat text in deep links
Biometrics = local lock, not authorisation
Deletion (stores)
In-app deletion (Apple and Google)
Plus a working web deletion page (Google)
Notes: PROPOSED CONTRACT: sign-in (password or invitation key reuse verification) → server issues short-lived access token + refresh credential tied to a device record → app stores the refresh credential in Expo SecureStore → every API call carries the access token; server checks account epoch (or equivalent) → refresh rotates atomically with reuse detection → logout revokes the device; sign-out-everywhere, password change and recovery revoke all devices.
SECURESTORE FACTS (docs.expo.dev, fetched 2026-09-15): data is not preserved on Android uninstall; on iOS it can persist across reinstall with the same bundle ID (do not rely on it); large payloads can be rejected — historically some iOS releases refused values above ~2048 bytes. So: store small credentials only, never transcripts; treat unreadable entries as re-authentication; verify the session at launch; uninstall is not a server logout.
Biometrics: optional local app lock only; never a replacement for server authorisation or recovery.
Recovery codes: shown only on deliberate issuance; never in analytics, logs or caches; explain copy/save choices.
DEEP LINKS: verified HTTPS universal/app links for defined routes; re-check authorisation after open; never put passwords, keys, tokens, chat text or recovery codes in links. Social login is out of MVP (system browser + authorisation code/PKCE if added).
DELETION: Apple guideline 5.1.1(v) and its account-deletion page (checked 2026-09-15) require in-app initiation of account deletion when the app supports account creation; Google Play (checked 2026-09-15) requires an in-app path AND a functional web link resource to request account and data deletion. The existing authenticated JSON endpoint alone is not the complete store deliverable.
SOURCES (repository paths are relative to the root): docs/MOBILE-ROADMAP.md §5 · docs.expo.dev SecureStore (checked 2026-09-15) · Apple 5.1.1(v) · Google Play account deletion (checked 2026-09-15)
BASELINE: branch fixes/launch-readiness-20260911, HEAD 1ed17eb5748d948a541f0e76a7fabcddd094534d plus the uncommitted working tree; deck prepared 2026-09-15.

## Slide 7
STREAMING, CANCELLATION, RECONNECTS AND BACKGROUND
Phones drop connections; turns must not duplicate
docs/MOBILE-ROADMAP.md §6 · backend/app/api/routes/chat.py (SSE start/delta/end/memory/error) · docs/PROJECT-REPORT.md §7
Mobile · 7
Send
request ID + fingerprint
Claim turn
durable record · lease
Stream
safe frame parsing
Finished
completion state
Backgrounded
network may stop
Reconcile on return
status + stored transcript · never resend
suspend
Duplicate prevention
Same key + same payload → same turn
Same key + new payload → rejected
Dedupe by server IDs, not text
Two devices never double-charge
Today: no replay, no idempotency key, one-worker locks.
Seamless resume is not promised without replay support.
Notes: TODAY (implemented): POST + SSE frames start, delta, end, memory, error; persisted completion metadata; NO durable generation ID, idempotency key or event replay; conversation locks serialise one worker only.
PROPOSED FLOW:
1. App creates a request ID (idempotency key) and sends it with a payload fingerprint. Same key + same payload returns the same operation; same key + different payload is rejected.
2. Server atomically claims a durable turn record (accepted/running/completed/truncated/interrupted/failed), with a lease for crashed workers.
3. App streams with chunk-boundary-safe UTF-8 and frame parsing, explicit abort and cleanup.
4. On background/suspension: assume network and execution stop. On foreground: reconcile the operation via status + stored transcript. NEVER auto-resend the prompt.
5. Try again = explicit regeneration; Continue = new user turn; show when more allowance may be used. Deduplicate by server IDs, never by message text. Two devices retrying at once must not create two charges for one operation.
Full replayable SSE is optional for MVP if reconciliation is safe; do not advertise seamless resume without replay. Guaranteed completion while the app is closed would need a durable server job, not a phone background task.
TESTS: final delta combined with finish reason, partial frames, missing terminal events, post-answer memory errors, server vs client timeouts (35 s provider, 50 s web client today), Wi-Fi→cellular, airplane mode, OS termination.
SOURCES (repository paths are relative to the root): docs/MOBILE-ROADMAP.md §6 · backend/app/api/routes/chat.py (SSE start/delta/end/memory/error) · docs/PROJECT-REPORT.md §7
BASELINE: branch fixes/launch-readiness-20260911, HEAD 1ed17eb5748d948a541f0e76a7fabcddd094534d plus the uncommitted working tree; deck prepared 2026-09-15.

## Slide 8
OFFLINE, CACHE, SYNC AND PRIVACY RULES
Server-authoritative, cache-light, account-isolated
docs/MOBILE-ROADMAP.md §7 · docs/PROJECT-REPORT.md §6 (memory, export, deletion)
Mobile · 8
Read offline
Cached chats, marked with last sync time
No offline AI
Sending is disabled — never queued to spend later
Writes need the server
Memory and goal edits confirm online; optimistic UI reverts
Encrypted, bounded cache
Size and age limits; no sensitive memories by default
Purge on exit
Logout, deletion, account switch or revocation wipe local data
Private telemetry
No prompts, facts, tokens or codes in logs or crashes
Notes: PROPOSED MVP RULES
- The server is the source of truth. A bounded, account-partitioned cache plus a local unsent draft.
- Offline: previously cached conversations can be read, with a clear "last synced" indicator. There is no offline model — AI sends are disabled offline, never silently queued for later spending.
- Storage: transcripts in an encrypted database or vetted encrypted store with platform-protected keys, explicit size/age bounds, backup policy and logout cleanup. SecureStore is not a database for large content. Do not cache sensitive memories by default without an explicit product decision.
- Analytics and crash reports must not contain prompts, facts, tokens or recovery material (vendor choice — or none — is an owner decision).
- Purge all account-specific cache and drafts on account switching, logout/deletion and confirmed revocation. Remove export temp files per a documented policy. Consider hiding chat text in app-switcher previews (test both platforms).
- Writes (memory, goals) require a connection and server confirmation; optimistic UI must revert on failure. Offline edits need versions/ETags and conflict detection first, so a mobile edit never overwrites a newer web correction. Future sync needs tombstones, cursor expiry and reconciliation; test restored device backups so deleted accounts or facts do not reappear.
SOURCES (repository paths are relative to the root): docs/MOBILE-ROADMAP.md §7 · docs/PROJECT-REPORT.md §6 (memory, export, deletion)
BASELINE: branch fixes/launch-readiness-20260911, HEAD 1ed17eb5748d948a541f0e76a7fabcddd094534d plus the uncommitted working tree; deck prepared 2026-09-15.

## Slide 9
DESIGN ADAPTATION AND ACCESSIBILITY
Sunshine & Ink on a phone
frontend/src/app/globals.css · docs/MOBILE-ROADMAP.md §8 · web screenshot 2026-09-15 (390px, desktop Chrome, mock model)
Mobile · 9
Team
Study
Career
Research
Writing
Travel
Finance
Home
Team
Memory
Goals
Study chat
Reply streams here; outcome is announced
Interrupted · Try again
Composer above keyboard
Home
Team
Memory
Goals
CONCEPT · NOT A SCREENSHOT
Web today · 390px · mock model
Must hold on phones
Ink on pink; deep pink text
Bottom tabs + stack chat
Keyboard-safe composer
Announce outcomes, not tokens
Text scaling, reduced motion
VoiceOver + TalkBack by people
Notes: LEFT: two CONCEPT wireframes drawn for this deck — they are not screenshots and no mobile UI exists. RIGHT: a real web screenshot at 390px (desktop Chrome, local dev, mock model) for reference.
PROPOSED DESIGN RULES: keep warm paper, yellow/pink fields, dark text, borders and large human artwork on discovery screens; a quiet reading surface in chat. Keep ink on pink and deep pink text #CC1757 (the contrast fix); never return to white on pink.
Navigation: native bottom tabs for Home, Team, Memory, Goals; Account clearly reachable; chat as a stack screen with history and standard back. Composer above the keyboard, safe areas respected, scroll position preserved, auto-follow new text only when the reader is near the bottom.
ACCESSIBILITY: platform text scaling; meaningful names/roles; announce reply outcomes and memory errors, not every token; recovery actions usable with VoiceOver and TalkBack; decorative art out of traversal, concise identity descriptions where informative; large fonts, reduced motion, landscape, small screens. Tablet scope decided separately.
ASSETS: bundle approved/licensed font files (licences to confirm — owner) and sized artwork (rights inventory missing — owner); keep text native and selectable; virtualise long transcripts; profile image decode and memory on older devices.
Evidence today covers the web only (25 axe scans, keyboard pass). Human VoiceOver/TalkBack and physical-device passes are required acceptance items.
SOURCES (repository paths are relative to the root): frontend/src/app/globals.css · docs/MOBILE-ROADMAP.md §8 · web screenshot 2026-09-15 (390px, desktop Chrome, mock model)
BASELINE: branch fixes/launch-readiness-20260911, HEAD 1ed17eb5748d948a541f0e76a7fabcddd094534d plus the uncommitted working tree; deck prepared 2026-09-15.

## Slide 10
NOTIFICATIONS, SAFETY, QUOTAS AND OBSERVABILITY
Push, AI safety and shared capacity
docs/MOBILE-ROADMAP.md §9 · Google Play AI-generated content policy (checked 2026-09-15) · docs/usage-limits.md
Mobile · 10
Push — optional
Only for a chosen use case
Needs a server job system
Generic payloads, no personal text
Unregister on logout
AFTER MVP
AI safety — required
In-app report / flag on replies
Rate-limited intake
Reviewer queue and response policy
Google Play policy, checked 2026-09-15
Load & quotas
One shared free-tier model quota
Measure before promising users
Keep one backend worker for now
Log versions and operation IDs, never text
Notes: NOTIFICATIONS (optional, after MVP): today's daily briefing is not a scheduled notification product. Push needs a chosen use case (e.g. opt-in reminders or a completed background job), a server scheduler/job system, device-token registration and revocation, timezone preferences, deduplication, quiet hours and delivery monitoring. Ask permission at the point of value; generic payloads without health/finance details or reply text; deep links recheck authorisation; logout/deletion unregister tokens.
SAFETY (store release requirement): Google Play's AI-generated content policy (fetched 2026-09-15) says apps that generate content using AI must contain in-app user reporting or flagging features so users can report offensive content without leaving the app, and developers should use reports to inform filtering/moderation. Build: in-app report action, rate-limited intake, authorised review queue, response policy, retention limits, content-minimising logs.
LOAD & QUOTAS: model capacity is server-wide and every account shares the upstream free-tier provider quota. Estimate demand from measured active users × turns/day × observed input/output/extraction usage plus peak simultaneous streams; allowance units are conservative, not provider tokens. Load-test admission, first-token latency, stream completion, SQL pool pressure, password hashing and extraction on the chosen host. Keep one worker until durable claims and distributed monitoring exist. Do not promise user counts before measuring.
OBSERVABILITY: agree targets first (latency percentiles, completed-turn rate, allowance rejections, crash-free sessions, backup age, restore time, operator response). Record app version, API version and operation IDs; never personal text. No current artifact establishes an SLA.
SOURCES (repository paths are relative to the root): docs/MOBILE-ROADMAP.md §9 · Google Play AI-generated content policy (checked 2026-09-15) · docs/usage-limits.md
BASELINE: branch fixes/launch-readiness-20260911, HEAD 1ed17eb5748d948a541f0e76a7fabcddd094534d plus the uncommitted working tree; deck prepared 2026-09-15.

## Slide 11
DEVICE, NETWORK AND SECURITY TEST MATRIX
Test on real devices and bad networks
docs/MOBILE-ROADMAP.md §10
Mobile · 11
Area | Must pass before release
Devices | Physical iPhone + Android · oldest supported OS · small screen · large text
Accounts | A→B switch · expired and deleted sessions · refresh replay · simultaneous recovery
Streaming | Wi-Fi→cellular · airplane mode · background · OS kill · duplicate taps · two devices
Data | Memory on/off · private isolation at provider input · export and deletion cleanup
Accessibility | VoiceOver and TalkBack by people · text scaling · reduced motion · focus after errors
Security | No secrets in logs, links or backups · token lifecycle · TLS · signed config
Quality | Full agent evaluation + real journeys · fingerprints · human adjudication
Evidence counts only against a named signed build and backend revision. Emulators and 390px web checks do not replace devices.
Notes: PROPOSED ACCEPTANCE MATRIX (evidence must name a signed build and backend revision):
- Devices: at least one physical iPhone and one Android phone; current and oldest supported OS in simulators/emulators; a small display; an older/memory-constrained Android; large text. Minimum OS support chosen after framework/device research (owner decision).
- Account isolation: A→B switching, stale caches, expired sessions, deleted account, sign-out-everywhere, password recovery, refresh-token replay, simultaneous recovery. A valid session must never reveal another account's state.
- Streaming: Wi-Fi→cellular, airplane mode, background/foreground, OS termination, slow response, idle stream, total cap, cancellation, failed extraction, duplicate taps, two-device overlap.
- Data: memory on/off, sensitive-candidate handling, manual correction protection, pinning, private specialist isolation at actual provider input, goal conflicts, export and deletion cleanup.
- UI/accessibility: VoiceOver/TalkBack, keyboard/safe areas, text scaling, reduced motion, focus after errors, portrait loading, long Markdown/code/tables.
- Security: no credentials in logs/deep links/backups; native token lifecycle; TLS; backend ownership checks; deletion; signed release configuration and dependency checks.
- Quality: complete release-agent evaluation plus short real personalised journeys, source/config fingerprints, human adjudication of contested judge outcomes.
A 390px web check does not count as a native-device pass; an automated scanner does not replace screen-reader testing.
SOURCES (repository paths are relative to the root): docs/MOBILE-ROADMAP.md §10
BASELINE: branch fixes/launch-readiness-20260911, HEAD 1ed17eb5748d948a541f0e76a7fabcddd094534d plus the uncommitted working tree; deck prepared 2026-09-15.

## Slide 12
SIGNING, BETA, SUBMISSION AND PRIVACY · STORE AND PLATFORM PAGES RECHECKED 2026-09-15
Store rules that shape the plan
developer.apple.com · developer.android.com · support.google.com (URLs in notes and appendix) — rechecked 2026-09-15
Mobile · 12
Apple
Build: Xcode 26+ with the iOS 26 SDK (since Apr 28, 2026)
AI sharing: disclose third-party AI and get explicit permission (5.1.2(i))
Deletion: account deletion inside the app (5.1.1(v))
Beta: external TestFlight builds need beta review
Privacy: App Privacy details from real data flows
Google Play
Target: Android 16 / API 36 from Aug 31, 2026
Deletion: in-app path and a working web page
AI content: in-app report or flag feature
Testing: 12 testers for 14 days on newer personal accounts
Privacy: Data safety form from real flows and SDKs
Owner holds developer accounts, app IDs and signing keys. Recheck every rule at submission time.
Notes: All of the following were fetched from official pages on 2026-09-15 (automated retrieval; re-verify at submission time):
- Apple, https://developer.apple.com/news/upcoming-requirements/ — apps uploaded to App Store Connect must be built with Xcode 26 or later using an SDK for iOS 26 (or iPadOS/tvOS/visionOS/watchOS 26); stated as effective since April 28, 2026. This is a BUILD requirement, not a minimum supported iOS version.
- Apple, https://developer.apple.com/app-store/review/guidelines/ — 5.1.2(i): clearly disclose where personal data is shared with third parties, including third-party AI, and obtain explicit permission first. 5.1.1(v): apps that support account creation must offer account deletion within the app.
- Apple, https://developer.apple.com/support/offering-account-deletion-in-your-app/ — deletion must be initiable in the app; deactivation alone is insufficient.
- Apple, https://developer.apple.com/help/app-store-connect/test-a-beta-version/invite-external-testers — external TestFlight builds go through TestFlight App Review (first build full review); up to 10,000 external testers per app.
- Google, https://developer.android.com/google/play/requirements/target-sdk — from August 31, 2026 new apps and updates must target Android 16 (API 36) or higher (phone apps); extension possible to November 1, 2026. Target API ≠ minimum supported Android.
- Google, https://support.google.com/googleplay/android-developer/answer/13327111 — apps enabling account creation must provide an in-app deletion path and a functional web link resource for account/data deletion requests.
- Google, https://support.google.com/googleplay/android-developer/answer/14151465 — personal developer accounts created after November 13, 2023 must run a closed test with at least 12 testers opted in continuously for at least 14 days before applying for production. Applicability depends on the owner's account type (owner decision; do not assume).
- Google, https://support.google.com/googleplay/android-developer/answer/13985936 — AI-generated content apps need in-app reporting/flagging.
Not rechecked on 2026-09-15: Apple App Privacy details and Google Data safety pages (carried from the 2026-09-13 roadmap); complete both from the actual app, backend and SDKs.
OWNERSHIP: the owner must hold Apple/Google developer accounts, bundle/application IDs, signing authority and recovery access. Separate dev/staging/production endpoints and signing profiles. Local iOS builds need Apple's toolchain; Windows alone is not the whole iOS release environment. Over-the-air updates must respect native compatibility and store policy. Store approval time is external and not guaranteed.
SOURCES (repository paths are relative to the root): developer.apple.com · developer.android.com · support.google.com (URLs in notes and appendix) — rechecked 2026-09-15
BASELINE: branch fixes/launch-readiness-20260911, HEAD 1ed17eb5748d948a541f0e76a7fabcddd094534d plus the uncommitted working tree; deck prepared 2026-09-15.

## Slide 13
PHASES, DEPENDENCIES AND EFFORT RANGES
Six phases, each with a gate to pass
docs/MOBILE-ROADMAP.md §12 · effort ranges are planning ranges under stated assumptions, not dates or quotes
Mobile · 13
0
Backend release closure
1–3 wk
Gates closed; staging + restore ready
1
Native feasibility
1–2 wk
Auth + stream + revoke on 2 devices
2
API & auth foundation
2–4 wk
Security & concurrency tests pass
3
Product MVP
3–5 wk
All journeys on staging
4
Release hardening
2–3 wk
No high-severity defects; signed build
5
Beta & stores
2–4+ wk
Store rules met; owner decides
Roughly 12–18 calendar weeks with one full-time React Native engineer, half-time backend, part-time design and QA; 16–24+ weeks if one engineer does everything.
Assumptions, not a schedule: English phone UI, no payments, push, voice or integrations. Re-estimate after Phase 1.
Notes: ASSUMPTIONS behind every range (from the roadmap): one experienced full-time React Native/TypeScript engineer; backend support about half-time; part-time design and QA; existing artwork reused; English phone UI; no billing, push, voice or integrations; prompt/provider behaviour largely retained; owner decisions, hardware, credentials and a usable staging host available when needed. Ranges overlap; they are not a priced quote. Do not turn them into promised dates or budgets.
PHASES
0. Backend release closure — 1–3 engineering weeks (operational waiting separate): staging verification of the implemented recovery/context/error fixes, quality acceptance, real-domain staging, backup/alert proof. Exit: critical findings closed; staging accounts and reliable rollback/restore.
1. Native feasibility — 1–2 weeks: small Expo development builds on both physical platforms; native auth design and streamed chat prototype. Exit: sign in, stream, interrupt, reconcile and revoke on both devices without duplicates or secret leakage.
2. API/auth foundation — 2–4 weeks: native session issuance/rotation, operation identity, conflict/error contract, pagination, shared types. Exit: security/concurrency tests pass; web authentication remains protected.
3. Product MVP — 3–5 weeks: Home/Team/Chat/History/Memory/Goals/Account, export/deletion, bounded cache, design/accessibility. Exit: all mapped journeys against staging with large text and scripted failures.
4. Release hardening — 2–3 weeks: device matrix, VoiceOver/TalkBack, load/quality verification, AI-sharing consent, AI reporting/support workflow. Exit: no unresolved high-severity defects; evidence tied to a signed candidate.
5. Beta and stores — 2–4+ calendar weeks: TestFlight/Play testing, store declarations/assets, monitored rollout. Exit: account-specific testing requirements met; owner release decision; store approval (external).
TOTALS under these assumptions: roughly 12–18 calendar weeks with overlap, plus hosting/account approvals and store cycles; a single engineer also owning backend, design and QA: roughly 16–24+ weeks. Re-estimate after Phase 1.
SOURCES (repository paths are relative to the root): docs/MOBILE-ROADMAP.md §12 · effort ranges are planning ranges under stated assumptions, not dates or quotes
BASELINE: branch fixes/launch-readiness-20260911, HEAD 1ed17eb5748d948a541f0e76a7fabcddd094534d plus the uncommitted working tree; deck prepared 2026-09-15.

## Slide 14
RISKS AND RELEASE GATES
Biggest risks and the gates that contain them
docs/MOBILE-ROADMAP.md §12–14 · docs/launch-rehearsal-2026-09-14.md · docs/quality-evidence-2026-09-15.md
Mobile · 14
Risk | What could go wrong | Containment
Auth concurrency | Token rotation races | Same DB locking + PostgreSQL race tests
Suspended streams | Lost or doubled turns | Device prototype · reconcile · never resend
Memory boundaries | Leaks across devices or accounts | Provider-input test in milestone 1
Shared quota | Free tier exhausted by phones | Measure demand before promising users
Store rules | AI consent, reporting, deletion | Built into MVP scope
Asset rights | No licence inventory | Owner assembles before submission
Release gates
Web gates closed and fixes committed
Feasibility passed on 2 platforms
Auth + operation contracts reviewed
Device, accessibility and security matrix on a signed build
Store forms, reports, deletion page live
Owner release decision
Notes: RISKS (from the roadmap) and mitigations:
- Recovery/auth concurrency on native tokens → apply the same database serialisation used for web recovery; PostgreSQL race tests for refresh rotation.
- Streaming during OS suspension → Phase 1 prototype on physical devices; server-side reconciliation; never auto-resend.
- Memory boundaries across devices → provider-input isolation test in the first milestone; account-partitioned cache.
- Shared free-tier provider quota → measure demand before promising users; keep allowances; consider owner decisions on capacity within the free tier.
- Platform accessibility → VoiceOver/TalkBack acceptance by people.
- Store AI and privacy requirements → AI-sharing consent, reporting workflow, deletion web page built into scope.
- Limited asset provenance → artwork and font rights inventory before submission (owner).
- Unmeasured answer quality → web quality acceptance precedes mobile exposure.
Adding voice, offline writes or payments requires a revised estimate.
RELEASE GATES for mobile (proposed): (1) web gates closed — quality accepted, real domain, remote backup, alert receipt, working tree committed; (2) Phase 1 feasibility passed on both platforms; (3) native auth/operation contracts security-reviewed; (4) device, accessibility and security matrix passed on a signed candidate; (5) store declarations, reporting workflow and deletion page live; (6) owner release decision.
SOURCES (repository paths are relative to the root): docs/MOBILE-ROADMAP.md §12–14 · docs/launch-rehearsal-2026-09-14.md · docs/quality-evidence-2026-09-15.md
BASELINE: branch fixes/launch-readiness-20260911, HEAD 1ed17eb5748d948a541f0e76a7fabcddd094534d plus the uncommitted working tree; deck prepared 2026-09-15.

## Slide 15
P0 · P1 · P2
Prioritised backlog
docs/MOBILE-ROADMAP.md §13
Mobile · 15
P0 · before native accounts
Staging proof of recovery and session fixes
Staging proof of memory-error and context bounds
API versioning + token threat model
Idempotency and durable turns
Device spike: auth, stream, revoke
P1 · MVP and stores
Native shell, chat, history
Memory, goals, Today, account
AI-sharing consent; export, deletion, purge
AI reports + triage; web deletion page
Device/security tests; signed builds
Store forms, beta, rollout
P2 · after demand
Push and background completion
Biometric lock, tablets
Localisation and RTL
Widgets, attachments, voice
Ask My Team, payments — separate design
Notes: P0 — before native account access
1. Verify the implemented R13-01 recovery and credential/session fixes in hosted staging (local PostgreSQL race tests already pass).
2. Verify the implemented R13-02/R13-03 memory-error propagation and aggregate context bounds in staging; reuse their regression cases for the native client.
3. Establish a staged API version/schema and a native token threat model; retain browser protections.
4. Add operation IDs, idempotency and durable turn ownership; specify reconciliation after uncertainty.
5. Prove physical-device streaming/auth/revocation on the chosen framework/toolchain.
P1 — required MVP and store delivery
6. Native shell, approved artwork/tokens, accessible keyboard-safe chat and history.
7. Memory/Goals/Today/Account parity and bounded account-isolated storage.
8. AI-sharing consent distinct from automatic learning; export/deletion and local purge.
9. AI response reporting with an owned support/triage workflow; external deletion resource.
10. Full device lifecycle/security tests, source-linked quality artifacts, signed builds and monitoring.
11. Store metadata, SDK/privacy declarations, beta requirements and controlled rollout.
P2 — after observed demand
Push reminders/background completion, biometric app lock, tablet optimisation, localisation/RTL, widgets, attachments, voice and selected integrations. Ask My Team stays off until its own design is approved. Payments need a separate product and policy phase.
SOURCES (repository paths are relative to the root): docs/MOBILE-ROADMAP.md §13
BASELINE: branch fixes/launch-readiness-20260911, HEAD 1ed17eb5748d948a541f0e76a7fabcddd094534d plus the uncommitted working tree; deck prepared 2026-09-15.

## Slide 16
START SMALL, PROVE THE RISKY PARTS
Recommended first milestone
docs/MOBILE-ROADMAP.md §14
Mobile · 16
1
Sign in to a synthetic staging account
2
Stream one Modeer reply
3
Drop the connection mid-reply
4
Reload the stored partial result
5
Try again — no duplicate spend
6
Sign out everywhere → session rejected
7
Private notes absent at provider input
Owner decisions
Team skills and staffing
Account mode and support policy
AI-sharing consent wording
Countries, ages, languages, min OS
Developer accounts and signing keys
Cache retention; analytics or none
Artwork and font rights
PROPOSED · AFTER WEB GATES
Notes: RECOMMENDED FIRST MILESTONE (proposed; only after critical backend/web gates): a two-platform prototype that signs into a synthetic staging account, streams one Modeer reply, loses connectivity mid-reply, reloads the authoritative partial result, retries without duplicate expenditure, and rejects the session after sign-out-everywhere. Include one private-memory isolation check at the actual provider input. At its review: choose the final framework/toolchain, approve the native auth and operation contracts, re-estimate using measured work, and only then start the full MVP.
OWNER DECISIONS NEEDED (do not assume from the web implementation): account mode and email-identity/support policy; automatic-memory default and AI-sharing consent wording; target countries, ages and languages; minimum OS/device coverage; hosting and provider capacity within the free tier and expected beta cohort; retention and offline-cache policy; artwork and font rights; who owns the Apple/Google developer accounts and signing keys; analytics/crash-reporting vendor or none; whether paid features ever belong in a later release; team staffing and framework experience.
SOURCES (repository paths are relative to the root): docs/MOBILE-ROADMAP.md §14
BASELINE: branch fixes/launch-readiness-20260911, HEAD 1ed17eb5748d948a541f0e76a7fabcddd094534d plus the uncommitted working tree; deck prepared 2026-09-15.

## Slide 17
APPENDIX
A1 · Verification sources for time-sensitive claims
Fetched 2026-09-15 via automated page retrieval · re-verify at implementation and submission
Mobile · 17
Claim | Source | Checked
Xcode 26 + iOS 26 SDK for uploads | developer.apple.com/news/upcoming-requirements | 2026-09-15
Third-party AI disclosure; in-app deletion | App Review Guidelines 5.1.2(i), 5.1.1(v) | 2026-09-15
TestFlight external review; 10,000 testers | App Store Connect help · invite external testers | 2026-09-15
Target API 36 from Aug 31, 2026 | developer.android.com · target-sdk | 2026-09-15
In-app + web account deletion | Play Console help 13327111 | 2026-09-15
12 testers × 14 days (newer personal accounts) | Play Console help 14151465 | 2026-09-15
AI content reporting in app | Play Console help 13985936 | 2026-09-15
expo/fetch streaming; SecureStore limits | docs.expo.dev (SDK 57 pages) | 2026-09-15
“Use a framework such as Expo” | reactnative.dev environment setup | 2026-09-13 · not rechecked
App Privacy · Data safety forms | Apple / Google help pages | 2026-09-13 · not rechecked
Notes: Checked 2026-09-15 (official pages):
1. https://developer.apple.com/news/upcoming-requirements/ — Xcode 26 / iOS 26 SDK since Apr 28, 2026.
2. https://developer.apple.com/app-store/review/guidelines/ — 5.1.2(i) third-party AI disclosure and explicit permission; 5.1.1(v) in-app account deletion.
3. https://developer.apple.com/support/offering-account-deletion-in-your-app/
4. https://developer.apple.com/help/app-store-connect/test-a-beta-version/invite-external-testers — TestFlight App Review for external builds; up to 10,000 external testers.
5. https://developer.android.com/google/play/requirements/target-sdk — API 36 from Aug 31, 2026 (extension to Nov 1, 2026).
6. https://support.google.com/googleplay/android-developer/answer/13327111 — in-app deletion + web resource.
7. https://support.google.com/googleplay/android-developer/answer/14151465 — 12 testers, 14 days, personal accounts created after Nov 13, 2023.
8. https://support.google.com/googleplay/android-developer/answer/13985936 — AI-generated content reporting.
9. https://docs.expo.dev/versions/latest/sdk/expo/ — expo/fetch streaming via resp.body.getReader() (SDK 57.0.0 page).
10. https://docs.expo.dev/versions/latest/sdk/securestore/ — uninstall behaviour; payload size caution.
NOT rechecked 2026-09-15 (documented 2026-09-13 in docs/MOBILE-ROADMAP.md): https://reactnative.dev/docs/environment-setup (fetch failed twice), Flutter architecture overview, Expo authentication and local builds guides, Apple App Privacy details, Google Data safety.
Limitation: pages were retrieved and summarised by an automated fetch tool; quoted requirements should be re-read directly before relying on them.
SOURCES (repository paths are relative to the root): Fetched 2026-09-15 via automated page retrieval · re-verify at implementation and submission
BASELINE: branch fixes/launch-readiness-20260911, HEAD 1ed17eb5748d948a541f0e76a7fabcddd094534d plus the uncommitted working tree; deck prepared 2026-09-15.

## Slide 18
APPENDIX
A2 · Native API work items in detail
docs/MOBILE-ROADMAP.md §5–7, §13
Mobile · 18
Item | Contract to define | Test before MVP
Native sessions | Access token TTL · rotating refresh · per-device record · family reuse detection | Replay, rotation race, revoke all
Operation identity | Idempotency key + payload fingerprint · durable turn · lease | Duplicate taps, two devices, worker crash
Reconciliation | Status endpoint · stored transcript as truth · no auto-resend | Background, OS kill, airplane mode
Errors | Stable codes: auth · allowance · provider limit · interrupted · memory | Each code surfaced and announced
Pagination | Cursor for conversations and messages | Large histories on old devices
Store support | AI report intake · web deletion page · API version header | Reports reach reviewers; page loads
Notes: See speaker notes on 'Reuse the backend; add what phones need' and 'Phones drop connections' for the full rationale. All items are proposed; none exist in the backend today.
SOURCES (repository paths are relative to the root): docs/MOBILE-ROADMAP.md §5–7, §13
BASELINE: branch fixes/launch-readiness-20260911, HEAD 1ed17eb5748d948a541f0e76a7fabcddd094534d plus the uncommitted working tree; deck prepared 2026-09-15.